## Template Retrospective
Sprint Retrospective | Iteration | 2
Project | Go Green
Group | 1
User Story | Task | Task Assigned to | Estimated Effort (in hours per person) | Actual Effort | Done | Notes
I as a user want my information to be fetched from the server | Make basic client | Max and Thom | 3 | 4 | Mostly | Work had to be redone after Sander's memo. Also, it was mostly Max and Dan Dan working on the code as Thom moved on to organising the directory and deliverables.
| Make basic server | Dan Dan and Jason | 3 | 4 | Yes | Work had to be redone after Sander's memo
I as a user want to interact with the app using a simple UI | Design GUI | Harshitaa | 2 | 2 | Yes
| Implement basic GUI in JavaFX | Harshitaa | 2 | 3 | Mostly
I as a developer I want the paperwork to be straightforward and properly organized | Organizing and working on paperwork | Thom | 2 | 3 | Yes
I as a developer want to organize the user data in a database | Make ER-schema for database | Thom | 1 | 0 | No | There was some doubt about what should go in the schema so work has not started
Main Problems Encountered
Problem 1 | Git issues
Description | Various git-related misconfigurations and ghost branches that kept rearing their ugly heads did slow our progress.
Reaction | Somewhere in the first halve of the week we decided on some conventions, mostly related to branching to keep our workflow professional
Problem 2 | Broken Maven dependencies
Description | Despite our best efforts to configure them neatly in Intellij, the dependencies were quite quirky.
Reactions | We have not resolved this problem yet and will discuss this Monday if needed.
Problem 3 | Obligatory from sockets to spring
Description | Though we thought we could just use sockets, a message from Sander revealed that we must use an api.
Reactions | Though we wasted some time, we are now well on our way to developing a working spring client-server interaction
Adjustments for next Sprint Plan
We will make sure that we know exactly what is expected from us so that we don't have to do things like rewriting socket networking code to use spring
We will anticipate issues with technologies we are unfamiliar with, as a substantial amount of time was wasted on problems with git and maven.