## Product
PRODUCT BACKLOG
| Feature | Priority | Sprint 1 | Sprint 2 | Sprint 3
| Server | M
1 | Server - Converts database into a web API. | M
2 | Server side - database model classes for features and users. | M
3 | Server side - API routes for login | S
4 | Server side - API routes for features. | M
GUI
5 | Wireframes displaying all different screen of the GUI
6 | GUI - login | S
7 | GUI - splash | S
8 | GUI - Features | M
9 | GUI - leaderboard | S
| Client | S
10 | Client - Consumes web API. | S
11 | Client - Interacts with the GUI.
Feature
12 | (Minimally) 5 features to track CO2 emissions. | M
13 | Badges - earned by reaching a certain amount of points on features. | M
Database
14 | ER diagram explaining the relation model. | S
15 | Database schema model. | S
16 | Database able to track (users, features, achievements, badges, CO2 emmisions) | M

## Sprint 1
| Feature | Priority | Tasks | Time estimation | Acceptance criteria
2 | Server side - database model classes for features and users. | M | Research how to interact between the database and spring classes
Model java classes based on the spring framework specifications
3 | Server side - API routes for login | S | Determine which routes are needed for the login functionality
configure these routes inside a spring controller
Write test code for the different route methods
4 | Server side - API routes for features. | M | Determine which routes are needed for the feature functionality
configure these routes inside a spring controller
Write test code for the different route methods
5 | Wireframes displaying all different screen of the GUI | S | Determine which screens the GUI should include
Create a wireframe for each screen
Describe the methods and actions behind each interactable element on the screen
6 | GUI - login | S | Transform the login wireframe into an JAVAFX screen
Connect all actions, events, methods to the GUI
8 | GUI - Features | M | Transform the feature screen wireframe into an JAVAFX screen
Connect all actions, events, methods to the GUI
14 | ER diagram explaining the relation model. | S | Determine which entities are required.
Model the entities and their properties.
Describe the relations between the different entities.
15 | Database schema model. | S | Make a schema model based on the entitiy diagram
normalize to NF3
16 | Database able to track (users, features, achievements, badges, CO2 emmisions) | M | Make a physical postgres database based on the database schema model