## Product
PRODUCT BACKLOG
| Feature | Priority | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5
Server
1 | Server - Converts database into a web API. | M
2 | Server side - database model classes for features and users. | M
3 | Server side - API routes for login | S
4 | Server side - API routes for features. | M
Server side - API routes for Achievements
S
S
M
S
S
| Client | S
10 | Client - Consumes web API. | S
11 | Client - Interacts with the GUI. | S
Feature
12 |  | M
13 | Achievements - earned by reaching a certain amount of points on features. | M
Database
14 | ER diagram explaining the relation model. | S
16 | Database able to track users, features, achievements | M
17 | Connect CO2 Emission API | S
18 | Reuse entities on both client and server side | C
19 | Meal API | S
20 | Working vegetarian meal feature with tests | M
21 | User authentication | S
| transport - bike | M
| Energy - solar panels | M
| Energy - temperature | M
| Local product | M
| CO2 API | M
| Meal API - server side implementation | S
| Friends | S
| final report - draft | M
| Presentation | M
| Test coverage > 85% | M
GUI
| Wireframes displaying all different screen of the GUI | S
| GUI - login | S
| GUI - Score + achievements | M
| GUI - Root | S
| GUI - profile | S
| GUI - compare | M
| GUI - meal improvments | S

## Sprint 2
| Feature | Priority | Tasks | Time estimation | Acceptance criteria
2 | Server side - database model classes for features and users. | M | Research how to interact between the database and spring classes
Model java classes based on the spring framework specifications
3 | Server side - API routes for login | S | Determine which routes are needed for the login functionality
configure these routes inside a spring controller
Write test code for the different route methods
4 | Server side - API routes for features. | M | Determine which routes are needed for the feature functionality
configure these routes inside a spring controller
Write test code for the different route methods
5 | Wireframes displaying all different screen of the GUI | S | Determine which screens the GUI should include
Create a wireframe for each screen
Describe the methods and actions behind each interactable element on the screen
6 | GUI - login | S | Transform the login wireframe into an JAVAFX screen
Connect all actions, events, methods to the GUI
8 | GUI - Features | M | Transform the feature screen wireframe into an JAVAFX screen
Connect all actions, events, methods to the GUI
14 | ER diagram explaining the relation model. | S | Determine which entities are required.
Model the entities and their properties.
Describe the relations between the different entities.
16 | Database able to track (users, features, achievements, badges, CO2 emmisions) | M | Make a physical postgres database based on the database schema model

## Sprint 3
| Feature | Priority | Tasks | Time estimation | Acceptance criteria
4 | Server side - API routes for features. | M | Describe all possible interactions with the features.
Create end points for all interactions
Implement all endpoints with database interaction
8 | GUI - Features | M | Implement the feature GUI based on the wireframe
Create a feature form
Create a feature controller
Connect the client controller to the features API endpoints
12 | (Minimally) 5 features to track CO2 emissions. | M | Research which options are tracked By the CO2 API
List all tracking options the application is going to provide
Alter the database based on the descriptions
Add the described tracking option.
13 | Achievements - earned by reaching a certain amount of points on features. | M | Describe the achievements to be included
Alter the database based on the descriptions
Add all the visual for the achievements (pictures, animations)
Create the entity, repository, controller.
Create all API end-points for the achievements
Connect the endpoint with the database
Copy the controller to the client-sde.
Create client side forms.
17 | Connect CO2 Emission API | M | Research which API to use
Research if it should be a direct call or save information in the database
Describe how it is going to be implemented in our application.
Describe other steps later.
| GUI - Main menu | S | Implement the main menu screen based on the wireframes.
Describe menu-items and application flow
Create all necessary forms
Create controller routes
| Reuse entities on both client and server side | C
| User authentication | S | Research how the security component in spring work.
Implement the security component on the server side.
Update the user entity based on the requirements of the component.
Update the user end points based on the requirements of the component.
Write test code for the server side endpoints.
Connect the login page and controller to the server side end points.
Write test code for the client side controller code.

## Sprint 4
| Feature | Priority | Tasks | Time estimation | Acceptance criteria
| Working vegetarian meal feature with tests | M | User authentication |  | Client is able to authenticate user
|  |  | Menu and feature GUI |  | User is able to navigate to the meal selection screen
|  |  | Meal api with connection to database. |  | User is able to select it's meal and collect points.
|  |  | Models and relations between users and features. |  | Database saves the points for a given user
|  |  | Test the controller code, database saving code, all routes. |  | Code coverage >80%
12 | (Minimally) 5 features to track CO2 emissions. | M | List all tracking options the application is going to provide
Alter the database based on the descriptions
Add the described tracking option.
13 | Achievements - earned by reaching a certain amount of points on features. | M | Describe the achievements to be included
Alter the database based on the descriptions
Add all the visual for the achievements (pictures, animations)
Create the entity, repository, controller.
Create all API end-points for the achievements
Connect the endpoint with the database
Copy the controller to the client-sde.
Create client side forms.
| GUI - Main menu | S | Implement the main menu screen based on the wireframes.
Describe menu-items and application flow
Create all necessary forms
Create controller routes
| Reuse entities on both client and server side | C
| User authentication | S | Research how the security component in spring work.
Implement the security component on the server side.
Update the user entity based on the requirements of the component.
Update the user end points based on the requirements of the component.
Write test code for the server side endpoints.
Connect the login page and controller to the server side end points.
Write test code for the client side controller code.

## Sprint 5
| Feature | Priority | Tasks | Time estimation | Acceptance criteria
12 | (Minimally) 5 features to track CO2 emissions. | M | List all tracking options the application is going to provide
Alter the database based on the descriptions
Add the described tracking option.
13 | Achievements - earned by reaching a certain amount of points on features. | M | Describe the achievements to be included
Alter the database based on the descriptions
Add all the visual for the achievements (pictures, animations)
Create the entity, repository, controller.
Create all API end-points for the achievements
Connect the endpoint with the database
Copy the controller to the client-sde.
Create client side forms.
| User authentication | S | Update the user end points based on the requirements of the component.
Write test code for the server side endpoints.
Connect the login page and controller to the server side end points.
Write test code for the client side controller code.
| transport - bike | M | Describe the screens
Create the entity
Create the controller
Create the tests
Create the connection with the CO2 API
| Energy - solar panels | M | Describe the screens
Create the entity
Create the controller
Create the tests
Create the connection with the CO2 API
| Energy - temperature | M | Describe the screens
Create the entity
Create the controller
Create the tests
Create the connection with the CO2 API
| Local product | M | Describe the screens
Create the entity
Create the controller
Create the tests
Create the connection with the CO2 API
| CO2 API | M | Describe the points to be used.
Describe the entities to use.
Describe the end points
Create the controller
Create end points
Create tests
| GUI - login | S
| GUI - Score + achievements | M
| GUI - Root | S
| GUI - profile | S
| GUI - compare | M